## Burn Down Chart
Project Title: Milestone 2 Scrum Release #: 1.1 Sprint #: 1.1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 1 | As a user I would like to login | Create database/data access | Jordan | 1 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Create login page | Jordan | 1 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Create login controller | Jordan | 1 | 0.25 | 0 | 0 | 0.3 | 0.85 | 0 | 0 | 0 | 0 | 0
|  |  | Implement authentication and login checks | Jordan | 2 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
| 2 | As a user I would like to register | Create database/data access | Antonio | 1 | 0.25 | 0 | 0 | 0.3 | 0.25 | 0 | 0 | 0 | 0 | 0
|  |  | Create register page | Antonio | 1 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Create a register controller | Antonio | 1 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Implement authentication and registration checks | Antonio | 2 | 0.25 | 0 | 0 | 0.3 | 1 | 0 | 0 | 0 | 0 | 0
| 3 | As a developer I would like to have wireframe diagrams that layout the design of the pages before implementation. | Create wireframes | Antonio | 1 | 0.25 | 0 | 0 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0
| 4 | As a developer I would like to plan and design my project ahead of time. | Create Design report/Scrum diagrams | Jordan/Antonio | 2 | 0.25 | 0 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 11.7 | 10.4 | 9.1 | 7.8 | 6.5 | 5.2 | 3.9 | 2.6 | 1.3 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 10.5 | 10.5 | 10.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time